## Gantt Chart
Activity | Start Date | Number of Days
Get the Equipments | 2015-02-25 | 2
Build the Arms Cover | 2015-02-28 | 3
Assemble the Armour | 2015-02-28 | 6
Design the Chest Piece | 2015-03-04 | 3
Prepare the Neck Piece | 2015-03-07 | 2
Design the Mask | 2015-03-10 | 3
Get the Cape & Gloves | 2015-03-13 | 2
Make the Boots | 2015-03-15 | 3
Stich the Suit | 2015-03-16 | 6
Attach the Belt | 2015-04-07 | 1
Test for Survival | 2015-03-24 | 7

## Sheet1
Activity | Start Date | Number of Days
Get the Equipments | 2015-02-25 | 2
Build the Arms Cover | 2015-02-28 | 3
Assemble the Armour | 2015-02-28 | 6
Design the Chest Piece | 2015-03-04 | 3
Prepare the Neck Piece | 2015-03-07 | 2
Design the Mask | 2015-03-10 | 3
Get the Cape & Gloves | 2015-03-13 | 2
Make the Boots | 2015-03-15 | 3
Stich the Suit | 2015-03-16 | 6
Attach the Belt | 2015-04-07 | 1
Test for Survival | 2015-03-24 | 7

## Sheet2
Particular | Estimated Quantity | Estimated Rate/Unit | Actual Quanity | Actual Rate/Unit | Estimated Amount | Actual Amount
Veneu Expanses
Plot/Hall/Room Rent | 1000 | 100 | 1000 | 110 | 100000 | 110000
Furniture Rent | 3000 | 10 | 3000 | 9 | 30000 | 27000
Electric and Other Electronic Equipements |  |  |  |  | 12000 | 15000
Tent/Decoration Expanses | 1000 | 20 | 10000 | 15 | 10000 | 8000
Other Miscelanious Expanses
|  |  |  | Total | 52000 | 50000
Refreshment Expanses
Food | 3000 | 200 | 3000 | 180 | 600000 | 540000
Drink | 3000 | 20 | 3000 | 15 | 60000 | 45000
Other
|  |  |  | Total | 660000 | 585000
Program Expenses
Presenters/ Performers /Staff Remunerstion | 100 | 1000 | 100 | 900 | 100000 | 90000
Presenters/ Performers /Staff Travelling Expanses | 100 | 200 | 100 | 185 | 20000 | 18500
Presenters/ Performers /Staff Accomodation | 100 | 100 | 100 | 85 | 10000 | 8500
Presenters/ Performers /Staff Clothing Expenses | 100 | 50 | 100 | 35 | 5000 | 3500
|  |  |  | Total | 135000 | 120500
Promotional Expenses
Web development | 1 | 25000 | 1 | 22000 | 25000 | 22000
Social Media Advertisement Expenses | 5 | 5000 | 5 | 3800 | 25000 | 19000
Print Media Advertisement Expenses | 12 | 10000 | 12 | 8500 | 120000 | 102000
Electonic Media Advertisement Expenses | 25 | 1000 | 25 | 750 | 25000 | 18750
Gift/ Momentous / Giveaway | 2000 | 15 | 2000 | 18 | 30000 | 36000
|  |  |  | Total | 225000 | 197750
Misceleneous Expenses
Name Tag /Budges | 100 | 50 | 100 | 50 | 5000 | 5000
Literature Printing | 2000 | 5 | 2000 | 4.5 | 10000 | 9000
Stickers / Banners | 30 | 100 | 30 | 100 | 3000 | 3000
Postage &Courier Charges | 0 |  | 0 |  | 0 | 0
stationery Expenese | 2000 | 1 | 2000 | 0.85 | 2000 | 1700
Telephone Charges | 0 |  | 0 |  | 0 | 0
Other Transportation Exp. | 1 | 5000 | 1 | 3500 | 5000 | 3500
Other Misceloanious Expenses | 0 |  | 0 |  | 0 | 0
|  |  |  | Total | 25000 | 22200
Grand Total Of Expenses |  |  |  |  | 1217000 | 1100450

## Sheet3
FROMULA
Text Formula
|  | UPPER | UPPER
|  | Lower | lower
|  | Proper | Upper
|  | len | omkar amberkar | 14
|  | Trim | omkar amberkar | omkar amberkar
|  | Concat | paresh | joshi | paresh joshi
|  | left | kalpesh kumar singh | kalpesh
|  | mid | kumar
|  | right | singh
Date Formula
|  | today | 2026-07-16
|  | now | 2026-07-16 20:05
|  | day | 16
|  | month | 7
|  | year | 2026
|  | date | 2026-07-16
|  | datedif | 2002-07-01 | 2026-07-16 | 8781
|  | Edate | 2026-07-11 | 12 | 2027-07-11
|  | text | Saturday